## Slide 1: 2022-2026 PhD Timeline
OCT 22
SEP 23
Year 1
2023
Qtr 1
Qtr 2
Qtr 4
Qtr 3
OCT 23
SEP 24
Year 2
2024
Qtr 5
Qtr 6
Qtr 8
Qtr 7
Spec.
Exam
(Mid Jun)
Paper 1
Paper 1
Mini-Prosp.
(May)
Today
(17 Aug)
Identify Topic
Coursework
Coursework
Coursework
Assumes a -paper format, where . Not every dissertation uses this format or results in only 3 publication-worthy contributions.
Notes:
Mini-prospectus: outlines the research problem, intended scope, relevant literature identified (to date), and initial work on the first paper. It’s purpose is to formally update the committee and, as appropriate, allow them to tailor Specialty Exam questions to align with your research.
The Specialty Exam: Format depends on your advisor. May be a “super-final” in the classes taken to complete specialty requirement. Often consists of questions drafted by committee prompted by reading your mini-prospectus.
Select Advisor
(Sept)
Identify Topic

## Slide 2: 2022-2026 PhD Timeline
OCT 24
SEP 25
Year 3
2025
Qtr 9
Qtr 10
Qtr 12
Qtr 11
Paper 2
OCT 25
Year 4
2026
Qtr 13
Qtr 14
Paper 3
Disn.
Def
(Jan/Feb)
MAR 26
Paper 3
Prosp.
Def
(Nov/Dec)
Notes:
Prospectus Defense: Required to become a PhD “Candidate”. Candidacy is required at least 12 months (ideally ~14 months) prior to defense.
Dissertation Defense: NLT week 8 of quarter 14